## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to AI Driven Code Review System using Python and React | MUST HAVE | No Dependency | Pradeesh P | 3- Completed
S1 | S1 | US-001 | Project Workflow, Architecture Diagram and Goal Documentation | MUST HAVE | System design UML tools Documentation tools | Pradeesh P | 3- Completed
S2 | S2 | US-001 | Agile Documentation Discussion (Agile Template, Defect Tracker, Unit Testing) | MUST HAVE | No Dependency | Pradeesh P | 3- Completed
S2 | S2 | US-001 | AI, Python, Flask, and Code Analysis Techniques Discussion | MUST HAVE | Flask framework ,code analysis concepts, LLMs | Pradeesh P | 3- Completed
S2 | S2 | US-001 | Code Review Use Case Research and Dataset Preparation | MUST HAVE | GitHub code repositories, Research | Pradeesh P | 3- Completed
S3 | S3 | US-001 | Python Practice and PySpark Environment Setup | MUST HAVE | VS Code | Pradeesh P | 3- Completed
S4 | S4 | US-001 | SQL Practice | MUST HAVE | Neondb | Pradeesh P | 3- Completed
S5 | S5 | US-001 | Project Discussion Module 1: Code Submission & Backend Setup(Data collection, Flask) backend setup) | MUST HAVE | VS Code | Pradeesh P | 3- Completed
S6 | S6 | US-001 | Project Discussion Module 2: Code Analysis & Feature Engineering | MUST HAVE | VS Code | Pradeesh P | 3- Completed
S7 | S7 | US-001 | Project Discussion Module 3: AI Feedback System & User Dashboard | MUST HAVE | OpenAI API | Pradeesh P | 3- Completed
S8 | S8 | US-001 | Project Discussion Module 4 Deployment, Security & Performance Enhancement | MUST HAVE | Cloud platform Replit | Pradeesh P | 3- Completed
S9 | S9 | US-001 | PPT Presentation practice and Project Demo Practice | MUST HAVE | PPT & Project | Pradeesh P | 3- Completed
S10 | S10 | US-001 | PPT Presentation practice and Project Demo shown to internal Team | MUST HAVE | PPT & Project | Pradeesh P | 3- Completed
S11 | S11 | US-001 | PPT Presentation practice and Project Demo shown to Infosys Team | MUST HAVE | PPT & Project | Pradeesh P | 2- In Progress

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 123 | 35 | 21 | 19 | 15 | 11 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Introduction to AI Driven Code Review System using Python and React | 2025-12-30 | 2025-12-31 | Pradeesh P | Others | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Project Workflow, Architecture Diagram and Goal Documentation | 2026-01-01 | 2026-01-02 | Pradeesh P | Others | 3- Completed | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 3 | Agile Documentation Discussion (Agile Template, Defect Tracker, Unit Testing) | 2026-01-03 | 2026-01-04 | Pradeesh P | Others | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 4 | AI, Python, Flask, and Code Analysis Techniques Discussion | 2026-01-05 | 2026-01-08 | Pradeesh P | Others | 3- Completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 5 | Code Review Use Case Research and Dataset Preparation | 2026-01-09 | 2026-01-10 | Pradeesh P | Others | 3- Completed | 12 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 6 | Python practice Kit Completion | 2026-01-11 | 2026-01-12 | Pradeesh P | Coding | 3- Completed | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 7 | SQL practice Kit Completion | 2026-01-15 | 2026-01-16 | Pradeesh P | Coding | 3- Completed | 10 | 3 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 8 | Project Discussion Module 1: Code Submission & Backend Setup(Data collection, Flask backend setup) | 2026-01-17 | 2026-01-22 | Pradeesh P | Coding | 3- Completed | 12 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 9 | Project Discussion Module 2: Code Analysis & Feature Engineering | 2026-01-23 | 2026-01-28 | Pradeesh P | Coding | 3- Completed | 12 | 4 | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 10 | Project Discussion Module 3: AI Feedback System & User Dashboard | 2026-01-29 | 2026-02-11 | Pradeesh P | Coding | 3- Completed | 10 | 3 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 11 | Project Discussion Module 4 Deployment, Security & Performance Enhancement | 2026-02-12 | 2026-02-20 | Pradeesh P | Coding | 3- Completed | 12 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 12 | PPT Presentation practice and Project Demo Practice | 2026-02-21 | 2026-02-23 | Pradeesh P | Others | 3- Completed | 10 | 3 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 13 | PPT Presentation practice and Project Demo shown to internal Team | 2026-02-25 | 2026-02-26 | Pradeesh P | Others | 3- Completed | 12 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 14 | PPT Presentation practice and Project Demo shown to Infoysis Team | 2026-02-28 |  | Pradeesh P | Others | 2- In Progress | 12 | 4 | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Lack of clarity on healthcare project requirements and data scope. | Conducted a detailed discussion with mentors and team
Sprint 1 | Day 4 | Lack of clarity on AWS architecture and workflow steps | Conducted a team brainstorming session and finalized AWS-based workflow and architecture diagram
Sprint 2 | Day 6 | Agile template confusion | Conducted a meeting where all doubts were clarified by the mentor.
Sprint 2 | Day 7 | Difficulty in identifying relevant code review metrics | Conducted additional research and consulted online resources to fill gaps.
Sprint 2 | Day 9 | Confusion in prioritizing features like syntax checking, AI feedback, database storage, and user dashboard | Created a priority matrix to evaluate and rank use cases based on importance.
Sprint 3 | Day 12 | Difficulty in Debugging Python Backend Scripts | Collaborated with mentor and peers to resolve coding and configuration issues
Sprint 4 | Day 16 | Performance Issues with Large Code Submissions | Optimized queries with mentor support
Sprint 5 | Day 23 | Challenges in Integrating Backend with Frontend | Scheduled focused debugging and integration sessions to resolve pipeline issues

## Retrospection
| Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-12-30 | 2026-01-06 | Pradeesh P | Reviewing project requirements andarchitecture documentation | Assuming project requirements are clear | Participating in discussions and meetings | Scheduled a review session with team and mentors to clarify project goals.
2 | Sprint 2 | 2026-01-07 | 2026-01-16 | Pradeesh P | Practicing Python and SQL regularly for data handling | Delaying review of tasks | Maintaining proper Agile documentation and task tracking | Completed Agile documents, dataset preparation, Python and SQL practice
3 | Sprint 3 | 2026-01-17 | 2026-02-11 | Pradeesh P | Developing Flask API and AI, AST modules step-by-step | Rushing AI and other modules implementation | Testing outputs after each implementation stage | Successfully implemented AI model using OpenAI via OpenRouter and database
4 | sprint 4 | 2026-02-12 | 2026-02-20 | Pradeesh P | Improving design and demo preparation and deploying project | Deployed project and PPT with excessive technical details | Focusing on key insights and results | Completed dashboard, predictive reports, internal demo, and final presentation preparation